## Yearly Plan 2024
Week | Project Setup | Continuous Integration | Continuous Delivery | Documentation
July | Create project plan |  |  |  | Difficulty
August | Setup infrastructure |  |  |  | Easy
September | Create scaffolding | Setup CI in GitHub | Setup CD in Azure |  | Medium
September |  |  | Deploy project | Create documentation | Hard
| Goals | Goals | Goals | Goals
| Create project plan | Setup CI | Setup CD | Create high quality documentation
| Setup project infrastructure |  | Deploy project

## Q3 2024
Week | Project Setup
2024-07-22 | Project Plan Spreadsheet
2024-08-01 | Create Trello board
2024-08-08 | Create common GitHub repository for common development
2024-08-15 | Create Azure account and subscription
2024-08-22 | Launch Azure Cloud Shell environment and create SSH key
2024-08-29 | Upload SSH keys to GitHub
Goals
Create project plan and estimation for team
Setup project start code and base structure
Difficulty
Easy
Medium
Hard

## Q4 2024
Week | Function to deliver | Documentation
2024-10-10 | Brainstorming with user and BA to define function, scope and estimation |  | Difficulty
2024-10-14 | Add Flask starter code to the project |  | Easy
2024-10-16 | Replace scaffolding code with Flask Machine Learning code |  | Medium
2024-10-20 | Authorize Azure App Service |  | Hard
2024-10-29 | Enable continuous deployment with Azure Pipelines
2024-11-04 | Add Azure Pipelines YAML based config file into GitHub
2024-11-11 | Authorize Azure App Service
11/120/2024 | Authorize Azure App Service | Create README for the project
11/31/2024 | Make prediction | Create video demo for the project
| Setup CD | Create high quality documentation
Deploy project